## Dashboard
Completed Percentage

## GanttChart
Asset Management
Top provider systems & supply co.,ltd
| Project Start Date |  |  | 2022-11-25 |  |  |  | Display Week | 1 |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23
| Project Overall Percentage |  |  | 69.78% | #DIV/0! | 4489150% | [5 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24
 | time axis 2022-11-21 to 2023-04-30
WBS | TASK | Assignee1 | Assignee2 | Team | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | Status | time axis 2022-11-21 to 2023-04-30
1 | Requirement Phase | [5 empty] | - |  | 100% | - | bar: 2022-11-21 to 2023-01-15
1.1 | Kick off Meeting | Puen |  | Lead |  | 2022-11-25 | 2022-11-25 | 1 | 100% | 1 | Completed
1.2 | Get requirement | Puen | New | Lead |  | 2022-11-28 | 2022-12-12 | 15 | 100% | 11 | Completed
1.3 | Provide Environment | bar: 2022-11-21 to 2023-01-15
1.3.1 | Server Development Environment | Guitar | Puen | DepOps |  | 2022-12-12 | 2022-12-16 | 5 | 100% | 5 | Completed
1.3.2 | Software Installation | Guitar |  | DepOps |  | 2022-12-12 | 2022-12-16 | 5 | 100% | 5 | Completed
2 | Analysis and Design Phase | [5 empty] | - |  | 100% | - | bar: 2022-11-21 to 2023-01-15
2.1 | Design and Mockup | bar: 2022-11-21 to 2023-01-15
2.1.1 | Create Wireframe | Aof | New | UX/UI |  | 2022-12-19 | 2022-12-23 | 5 | 100% | 5 | Completed
2.1.2 | Provide UX/UI (Mockup) | Aof | New | UX/UI |  | 2022-12-19 | 2023-01-06 | 19 | 100% | 15 | Completed
2.2 | Database Design | bar: 2022-11-21 to 2023-01-15
2.2.1 | Blueprint | Memmos | Puen | SA |  | 2023-01-09 | 2023-01-20 | 12 | 100% | 10 | Completed
2.2.2 | Provide Entity Relationship Diagram | New | Puen | Back-end |  | 2023-01-02 | 2023-01-13 | 12 | 100% | 10 | Completed
2.2.3 | Create Database and Tables | Memmos | Puen | Back-end |  | 2023-01-09 | 2023-01-20 | 12 | 100% | 10 | Completed
2.2.4 | Software Technical Specification | Memmos | Puen | SA |  | 2023-01-09 | 2023-01-20 | 12 | 100% | 10 | Completed
3 | Development Phase | [5 empty] | - |  | 70.78% | - | bar: 2022-11-21 to 2023-01-15
3.1 | Front-end | [7 empty] | 62.81% | bar: 2022-11-21 to 2023-01-15
3.1.1 | 65.0 เข้าสู่ระบบ | bar: 2022-11-21 to 2023-01-15
3.1.1.1 | . . . 65.0.0 เข้าสู่ระบบ | Aof |  | Front-end |  | 2023-01-23 | 2023-01-27 | 5 | 90% | 5 | Waiting for Test
3.1.1.2 | . . . 65.0.1 ลืมรหัสผ่าน | Aof |  | Front-end |  | 2023-01-23 | 2023-01-27 | 5 | 90% | 5 | Waiting for Test
3.1.2 | 65.1 dashboard งานบริหารงานทรัพย์สิน | bar: 2022-11-21 to 2023-01-15
3.1.2.1 | . . . 65.1.1 dashboard งานซ่อม | Aof |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 20% | 10 | In-Progress
3.1.3 | 65.2 รายการข้อมูลครุภัณฑ์ | bar: 2022-11-21 to 2023-01-15
3.1.3.1 | . . . 65.2.1 บันทึกครุภัณฑ์ | Nai |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 90% | 10 | Waiting for Test
3.1.3.2 | . . . 65.2.2 ดูรูปภาพเพิ่มเติมครุภัณฑ์ | Nai |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 90% | 10 | Waiting for Test
3.1.3.3 | . . . 65.2.3 คู่มือ/เอกสารแนบครุภัณฑ์ | Nai |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 90% | 10 | Waiting for Test
3.1.3.4 | . . . 65.2.4 ค่าเสื่อมราคาครุภัณฑ์ | Nai |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 90% | 10 | Waiting for Test
3.1.3.5 | . . . 65.2.5 รายละเอียดข้อมูลครุภัณฑ์ | Nai |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 90% | 10 | Waiting for Test
3.1.3.6 | . . . 65.2.7 แก้ไขข้อมูลครุภัณฑ์ | Nai |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 90% | 10 | Waiting for Test
3.1.3.7 | . . . 65.2.8 ลบข้อมูลครุภัณฑ์ | Nai |  | Front-end |  | 2023-01-30 | 2023-02-10 | 12 | 90% | 10 | Waiting for Test
3.1.4 | 65.3 ข้อมูลครุภัณฑ์หน่วยงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.4.1 | . . . 65.3.1 ดูข้อมูลครุภัณฑ์หน่วยงาน | Nai |  | Front-end |  | 2023-02-13 | 2023-02-17 | 5 | 90% | 5 | Waiting for Test
3.1.5 | 5.4 รายการข้อมูลครุภัณฑ์เป็นชุด | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.5.1 | . . . 65.4.1 บันทึกครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.5.2 | . . . 65.4.2 ดูรูปภาพเพิ่มเติมครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.5.3 | . . . 65.4.3 ส่วนประกอบย่อยครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.5.4 | . . . 65.4.4 คู่มือ/เอกสารแนบครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.5.5 | . . . 65.4.5 ค่าเสื่อมราคาครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.5.6 | . . . 65.4.6 รายละเอียดข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.5.7 | . . . 65.4.7 แก้ไขข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.5.8 | . . . 65.4.8 ลบข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Front-end |  | 2023-02-13 | 2023-02-22 | 10 | 90% | 8 | Waiting for Test
3.1.6 | 65.5 ข้อมูลครุภัณฑ์เป็นชุด(หน่วยงาน) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.6.1 | . . . 65.5.1 ดูข้อมูลครุภัณฑ์เป็นชุด(หน่วยงาน) | Nai |  | Front-end |  | 2023-02-22 | 2023-02-24 | 3 | 90% | 3 | Waiting for Test
3.1.7 | 65.6 รายการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.7.1 | . . . 65.6.1 รายละเอียดโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-02-27 | 2023-03-03 | 5 | 90% | 5 | Waiting for Test
3.1.7.2 | . . . 65.6.2 บันทึกโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-02-27 | 2023-03-03 | 5 | 90% | 5 | Waiting for Test
3.1.7.3 | . . . 65.6.3 แก้ไขโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-02-27 | 2023-03-03 | 5 | 90% | 5 | Waiting for Test
3.1.7.4 | . . . 65.6.4 ยกเลิกโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-02-27 | 2023-03-03 | 5 | 90% | 5 | Waiting for Test
3.1.8 | 65.7 รายการอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.8.1 | . . . 65.7.1 รายละเอียดขออนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-06 | 2023-03-14 | 9 | 90% | 7 | Waiting for Test
3.1.8.2 | . . . 65.7.2 รายละเอียดการอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-06 | 2023-03-14 | 9 | 90% | 7 | Waiting for Test
3.1.8.3 | . . . 65.7.3 ไม่อนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์(สาเหตุแบบหลายรายการ) | Nai |  | Front-end |  | 2023-03-06 | 2023-03-14 | 9 | 90% | 7 | Waiting for Test
3.1.8.4 | . . . 65.7.4 ไม่อนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Front-end |  | 2023-03-06 | 2023-03-14 | 9 | 90% | 7 | Waiting for Test
3.1.8.5 | . . . 65.7.5 ยืนยันอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-06 | 2023-03-14 | 9 | 90% | 7 | Waiting for Test
3.1.8.6 | . . . 65.7.6 แก้ไขรายการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-06 | 2023-03-14 | 9 | 90% | 7 | Waiting for Test
3.1.9 | 65.8 ประวัติการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.9.1 | . . . 65.8.1 รายละเอียดประวัติการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Aof |  | Front-end |  | 2023-03-14 | 2023-03-15 | 2 | 90% | 2 | Waiting for Test
3.1.10 | 65.9 รายการยืม-คืนครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.10.1 | . . . 65.9.1 รายละเอียดการยืมครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-16 | 2023-03-24 | 9 | 90% | 7 | Waiting for Test
3.1.10.2 | . . . 65.9.2 บันทึกใบยืมครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-16 | 2023-03-24 | 9 | 90% | 7 | Waiting for Test
3.1.10.3 | . . . 65.9.3 บันทึกใบคืนครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-16 | 2023-03-24 | 9 | 90% | 7 | Waiting for Test
3.1.10.4 | . . . 65.9.4 แก้ไขใบยืมครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-16 | 2023-03-24 | 9 | 90% | 7 | Waiting for Test
3.1.10.5 | . . . 65.9.5 ยกเลิกใบยืมครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-16 | 2023-03-24 | 9 | 90% | 7 | Waiting for Test
3.1.11 | 65.10 รายการอนุมัติยืมครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.11.1 | . . . 65.10.1 รายละเอียดอนุมัติยืมครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-27 | 2023-03-31 | 5 | 90% | 5 | Waiting for Test
3.1.11.2 | . . . 65.10.2 รายละเอียดการอนุมัติยืมครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-27 | 2023-03-31 | 5 | 90% | 5 | Waiting for Test
3.1.11.3 | . . . 65.10.3 ไม่อนุมัติยืมครุภัณฑ์(สาเหตุแบบหลายรายการ) | Nai |  | Front-end |  | 2023-03-27 | 2023-03-31 | 5 | 90% | 5 | Waiting for Test
3.1.11.4 | . . . 65.10.4 ไม่อนุมัติยืมครุภัณฑ์(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Front-end |  | 2023-03-27 | 2023-03-31 | 5 | 90% | 5 | Waiting for Test
3.1.11.5 | . . . 65.10.5 ยืนยันอนุมัติยืมครุภัณฑ์ | Nai |  | Front-end |  | 2023-03-27 | 2023-03-31 | 5 | 90% | 5 | Waiting for Test
3.1.12 | 65.11 ประวัติการยืมครุภัณฑ์(ตามเลขที่ใบยืมครุภัณฑ์) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.12.1 | . . . 65.11.1 รายละเอียดประวัติการยืม(ตามเลขที่ใบยืมครุภัณฑ์) | Nai |  | Front-end |  | 2023-04-03 | 2023-04-07 | 5 | 90% | 5 | Waiting for Test
3.1.13 | 65.12 รายการตรวจรับคืนครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.13.1 | . . . 65.12.1 ตรวจรับการคืนครุภัณฑ์ | Nai |  | Front-end |  | 2023-04-03 | 2023-04-07 | 5 | 90% | 5 | Waiting for Test
3.1.13.2 | . . . 65.12.2 รายละเอียดการตรวจรับคืนครุภัณฑ์ | Nai |  | Front-end |  | 2023-04-03 | 2023-04-07 | 5 | 90% | 5 | Waiting for Test
3.1.14 | 65.13 รายการแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.14.1 | . . . 65.13.1 บันทึกรายการแจ้งซ่อม | Nai |  | Front-end |  | 2023-04-10 | 2023-04-14 | 5 | 90% | 5 | Waiting for Test
3.1.14.2 | . . . 65.13.2 แก้ไขรายการแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-05 | 2023-07-05 | 1 | 20% | 1 | In-Progress
3.1.14.3 | . . . 65.13.3 ยกเลิกรายการแจ้งซ่อม(กรณียังไม่รับงาน) | Nai |  | Front-end |  | 2023-07-06 | 2023-07-06 | 1 | 0% | 1 | To-Do
3.1.14.4 | . . . 65.13.4 รายละเอียดการแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-07 | 2023-07-07 | 1 | 0% | 1 | To-Do
3.1.15 | 65.14 รายการแจ้งซ่อม(ศูนย์ซ่อม) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.15.1 | . . . 65.14.1 ดูรายละเอียดแจ้งซ่อม/รับงานแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-10 | 2023-07-13 | 4 | 0% | 4 | To-Do
3.1.15.2 | . . . 65.14.1.1 ไม่รับงาน | Nai |  | Front-end |  | 2023-07-10 | 2023-07-13 | 4 | 0% | 4 | To-Do
3.1.15.3 | . . . 65.14.2 ลงบันทึกแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-10 | 2023-07-13 | 4 | 0% | 4 | To-Do
3.1.15.4 | . . . 65.14.3 จ้างซ่อมภายนอก | Nai |  | Front-end |  | 2023-07-10 | 2023-07-13 | 4 | 0% | 4 | To-Do
3.1.15.5 | . . . 65.14.4 แก้ไขแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-10 | 2023-07-13 | 4 | 0% | 4 | To-Do
3.1.16 | 65.15 รายการตรวจสอบจ้างซ่อมภายนอก | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.16.1 | . . . 65.15.1 รายละเอียดจ้างซ่อมภายนอก | Nai |  | Front-end |  | 2023-07-14 | 2023-07-17 | 4 | 0% | 2 | To-Do
3.1.17 | 65.16 รายการอนุมัติแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.17.1 | . . . 65.16.1 ข้อมูลอนุมัติการแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-18 | 2023-07-18 | 1 | 0% | 1 | To-Do
3.1.17.2 | . . . 65.16.2 ไม่อนุมัติแจ้งซ่อม(สาเหตุแบบหลายรายการ) | Nai |  | Front-end |  | 2023-07-19 | 2023-07-19 | 1 | 0% | 1 | To-Do
3.1.17.3 | . . . 65.16.3 ไม่อนุมัติแจ้งซ่อม(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Front-end |  | 2023-07-20 | 2023-07-20 | 1 | 0% | 1 | To-Do
3.1.17.4 | . . . 65.16.4 ยืนยันอนุมัติแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-21 | 2023-07-21 | 1 | 0% | 1 | To-Do
3.1.18 | 65.17 บันทึกปิดงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.18.1 | . . . 65.17.1 บันทึกปิดงาน | Nai |  | Front-end |  | 2023-07-24 | 2023-07-24 | 1 | 0% | 1 | To-Do
3.1.19 | 65.18 ตรวจรับงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.19.1 | . . . 65.18.1 ตรวจรับงาน | Nai |  | Front-end |  | 2023-07-25 | 2023-07-26 | 2 | 0% | 2 | To-Do
3.1.20 | 65.19 รายการประวัติการแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.1.20.1 | . . . 65.19.1 รายละเอียดประวัติแจ้งซ่อม | Nai |  | Front-end |  | 2023-07-27 | 2023-07-28 | 2 | 0% | 2 | To-Do
3.1.20.2 | . . . 65.19.2 รายละเอียดประวัติแจ้งซ่อมตามครุภัณฑ์ | Nai |  | Front-end |  | 2023-07-31 | 2023-08-01 | 2 | 0% | 2 | To-Do
3.1.21 | 65.20 Mail Template | Aof | Nai | Front-end |  |  | - |  | 0% | - | To-Do
3.1.22 | 65.21 Master Data | Aof | Nai | Front-end |  | 2023-08-02 | 2023-08-04 | 3 | 20% | 3 | In-Progress
3.2 | Back-end | [7 empty] | 78.75% | bar: 2022-11-21 to 2023-01-15
3.2.1 | 65.0 เข้าสู่ระบบ | bar: 2022-11-21 to 2023-01-15
3.2.1.1 | . . . 65.0.0 เข้าสู่ระบบ | Aof |  | Back-end |  | 2023-01-30 | 2023-02-03 | 5 | 80% | 5 | Waiting for Interface
3.2.1.2 | . . . 65.0.1 ลืมรหัสผ่าน | Aof |  | Back-end |  | 2023-01-30 | 2023-02-03 | 5 | 80% | 5 | Waiting for Interface
3.2.2 | 65.1 dashboard งานบริหารงานทรัพย์สิน | bar: 2022-11-21 to 2023-01-15
3.2.2.1 | . . . 65.1.1 dashboard งานซ่อม | Aof |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 0% | 10 | To-Do
3.2.3 | 65.2 รายการข้อมูลครุภัณฑ์ | bar: 2022-11-21 to 2023-01-15
3.2.3.1 | . . . 65.2.1 บันทึกครุภัณฑ์ | Nai |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 80% | 10 | Waiting for Interface
3.2.3.2 | . . . 65.2.2 ดูรูปภาพเพิ่มเติมครุภัณฑ์ | Nai |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 80% | 10 | Waiting for Interface
3.2.3.3 | . . . 65.2.3 คู่มือ/เอกสารแนบครุภัณฑ์ | Nai |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 80% | 10 | Waiting for Interface
3.2.3.4 | . . . 65.2.4 ค่าเสื่อมราคาครุภัณฑ์ | Nai |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 80% | 10 | Waiting for Interface
3.2.3.5 | . . . 65.2.5 รายละเอียดข้อมูลครุภัณฑ์ | Nai |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 80% | 10 | Waiting for Interface
3.2.3.6 | . . . 65.2.7 แก้ไขข้อมูลครุภัณฑ์ | Nai |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 80% | 10 | Waiting for Interface
3.2.3.7 | . . . 65.2.8 ลบข้อมูลครุภัณฑ์ | Nai |  | Back-end |  | 2023-02-06 | 2023-02-17 | 12 | 80% | 10 | Waiting for Interface
3.2.4 | 65.3 ข้อมูลครุภัณฑ์หน่วยงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.4.1 | . . . 65.3.1 ดูข้อมูลครุภัณฑ์หน่วยงาน | Nai |  | Back-end |  | 2023-02-20 | 2023-02-24 | 5 | 80% | 5 | Waiting for Interface
3.2.5 | 65.4 รายการข้อมูลครุภัณฑ์เป็นชุด | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.5.1 | . . . 65.4.1 บันทึกครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.5.2 | . . . 65.4.2 ดูรูปภาพเพิ่มเติมครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.5.3 | . . . 65.4.3 ส่วนประกอบย่อยครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.5.4 | . . . 65.4.4 คู่มือ/เอกสารแนบครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.5.5 | . . . 65.4.5 ค่าเสื่อมราคาครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.5.6 | . . . 65.4.6 รายละเอียดข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.5.7 | . . . 65.4.7 แก้ไขข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.5.8 | . . . 65.4.8 ลบข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-02-20 | 2023-03-01 | 10 | 80% | 8 | Waiting for Interface
3.2.6 | 65.5 ข้อมูลครุภัณฑ์เป็นชุด(หน่วยงาน) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.6.1 | . . . 65.5.1 ดูข้อมูลครุภัณฑ์เป็นชุด(หน่วยงาน) | Nai |  | Back-end |  | 2023-03-01 | 2023-03-03 | 3 | 80% | 3 | Waiting for Interface
3.2.7 | 65.6 รายการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.7.1 | . . . 65.6.1 รายละเอียดโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-06 | 2023-03-10 | 5 | 80% | 5 | Waiting for Interface
3.2.7.2 | . . . 65.6.2 บันทึกโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-06 | 2023-03-10 | 5 | 80% | 5 | Waiting for Interface
3.2.7.3 | . . . 65.6.3 แก้ไขโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-06 | 2023-03-10 | 5 | 80% | 5 | Waiting for Interface
3.2.7.4 | . . . 65.6.4 ยกเลิกโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-06 | 2023-03-10 | 5 | 80% | 5 | Waiting for Interface
3.2.8 | 65.7 รายการอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.8.1 | . . . 65.7.1 รายละเอียดขออนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-13 | 2023-03-21 | 9 | 80% | 7 | Waiting for Interface
3.2.8.2 | . . . 65.7.2 รายละเอียดการอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-13 | 2023-03-21 | 9 | 80% | 7 | Waiting for Interface
3.2.8.3 | . . . 65.7.3 ไม่อนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์(สาเหตุแบบหลายรายการ) | Nai |  | Back-end |  | 2023-03-13 | 2023-03-21 | 9 | 80% | 7 | Waiting for Interface
3.2.8.4 | . . . 65.7.4 ไม่อนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Back-end |  | 2023-03-13 | 2023-03-21 | 9 | 80% | 7 | Waiting for Interface
3.2.8.5 | . . . 65.7.5 ยืนยันอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-13 | 2023-03-21 | 9 | 80% | 7 | Waiting for Interface
3.2.8.6 | . . . 65.7.6 แก้ไขรายการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-13 | 2023-03-21 | 9 | 80% | 7 | Waiting for Interface
3.2.9 | 65.8 ประวัติการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.9.1 | . . . 65.8.1 รายละเอียดประวัติการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Aof |  | Back-end |  | 2023-03-21 | 2023-03-22 | 2 | 80% | 2 | Waiting for Interface
3.2.10 | 65.9 รายการยืม-คืนครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.10.1 | . . . 65.9.1 รายละเอียดการยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-23 | 2023-03-31 | 9 | 80% | 7 | Waiting for Interface
3.2.10.2 | . . . 65.9.2 บันทึกใบยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-23 | 2023-03-31 | 9 | 80% | 7 | Waiting for Interface
3.2.10.3 | . . . 65.9.3 บันทึกใบคืนครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-23 | 2023-03-31 | 9 | 80% | 7 | Waiting for Interface
3.2.10.4 | . . . 65.9.4 แก้ไขใบยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-23 | 2023-03-31 | 9 | 80% | 7 | Waiting for Interface
3.2.10.5 | . . . 65.9.5 ยกเลิกใบยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-03-23 | 2023-03-31 | 9 | 80% | 7 | Waiting for Interface
3.2.11 | 65.10 รายการอนุมัติยืมครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.11.1 | . . . 65.10.1 รายละเอียดอนุมัติยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-04-03 | 2023-04-07 | 5 | 80% | 5 | Waiting for Interface
3.2.11.2 | . . . 65.10.2 รายละเอียดการอนุมัติยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-04-03 | 2023-04-07 | 5 | 80% | 5 | Waiting for Interface
3.2.11.3 | . . . 65.10.3 ไม่อนุมัติยืมครุภัณฑ์(สาเหตุแบบหลายรายการ) | Nai |  | Back-end |  | 2023-04-03 | 2023-04-07 | 5 | 80% | 5 | Waiting for Interface
3.2.11.4 | . . . 65.10.4 ไม่อนุมัติยืมครุภัณฑ์(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Back-end |  | 2023-04-03 | 2023-04-07 | 5 | 80% | 5 | Waiting for Interface
3.2.11.5 | . . . 65.10.5 ยืนยันอนุมัติยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-04-03 | 2023-04-07 | 5 | 80% | 5 | Waiting for Interface
3.2.12 | 65.11 ประวัติการยืมครุภัณฑ์(ตามเลขที่ใบยืมครุภัณฑ์) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.12.1 | . . . 65.11.1 รายละเอียดประวัติการยืม(ตามเลขที่ใบยืมครุภัณฑ์) | Nai |  | Back-end |  | 2023-04-10 | 2023-04-14 | 5 | 80% | 5 | Waiting for Interface
3.2.13 | 65.12 รายการตรวจรับคืนครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.13.1 | . . . 65.12.1 ตรวจรับการคืนครุภัณฑ์ | Nai |  | Back-end |  | 2023-04-10 | 2023-04-14 | 5 | 80% | 5 | Waiting for Interface
3.2.13.2 | . . . 65.12.2 รายละเอียดการตรวจรับคืนครุภัณฑ์ | Nai |  | Back-end |  | 2023-04-10 | 2023-04-14 | 5 | 80% | 5 | Waiting for Interface
3.2.14 | 65.13 รายการแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.14.1 | . . . 65.13.1 บันทึกรายการแจ้งซ่อม | Nai |  | Back-end |  | 2023-04-17 | 2023-04-21 | 5 | 80% | 5 | Waiting for Interface
3.2.14.2 | . . . 65.13.2 แก้ไขรายการแจ้งซ่อม | Nai |  | Back-end |  | 2023-04-17 | 2023-04-21 | 5 | 80% | 5 | Waiting for Interface
3.2.14.3 | . . . 65.13.3 ยกเลิกรายการแจ้งซ่อม(กรณียังไม่รับงาน) | Nai |  | Back-end |  | 2023-04-17 | 2023-04-21 | 5 | 80% | 5 | Waiting for Interface
3.2.14.4 | . . . 65.13.4 รายละเอียดการแจ้งซ่อม | Nai |  | Back-end |  | 2023-04-17 | 2023-04-21 | 5 | 80% | 5 | Waiting for Interface
3.2.15 | 65.14 รายการแจ้งซ่อม(ศูนย์ซ่อม) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.15.1 | . . . 65.14.1 ดูรายละเอียดแจ้งซ่อม/รับงานแจ้งซ่อม | Nai |  | Back-end |  | 2023-06-12 | 2023-06-16 | 5 | 80% | 5 | Waiting for Interface
3.2.15.2 | . . . 65.14.1.1 ไม่รับงาน | Nai |  | Back-end |  | 2023-06-12 | 2023-06-16 | 5 | 80% | 5 | Waiting for Interface
3.2.15.3 | . . . 65.14.2 ลงบันทึกแจ้งซ่อม | Nai |  | Back-end |  | 2023-06-12 | 2023-06-16 | 5 | 80% | 5 | Waiting for Interface
3.2.15.4 | . . . 65.14.3 จ้างซ่อมภายนอก | Nai |  | Back-end |  | 2023-06-12 | 2023-06-16 | 5 | 80% | 5 | Waiting for Interface
3.2.15.5 | . . . 65.14.4 แก้ไขแจ้งซ่อม | Nai |  | Back-end |  | 2023-06-12 | 2023-06-16 | 5 | 80% | 5 | Waiting for Interface
3.2.16 | 65.15 รายการตรวจสอบจ้างซ่อมภายนอก | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.16.1 | . . . 65.15.1 รายละเอียดจ้างซ่อมภายนอก | Nai |  | Back-end |  | 2023-06-19 | 2023-06-23 | 5 | 80% | 5 | Waiting for Interface
3.2.17 | 65.16 รายการอนุมัติแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.17.1 | . . . 65.16.1 ข้อมูลอนุมัติการแจ้งซ่อม | Nai |  | Back-end |  | 2023-06-19 | 2023-06-23 | 5 | 80% | 5 | Waiting for Interface
3.2.17.2 | . . . 65.16.2 ไม่อนุมัติแจ้งซ่อม(สาเหตุแบบหลายรายการ) | Nai |  | Back-end |  | 2023-06-19 | 2023-06-23 | 5 | 80% | 5 | Waiting for Interface
3.2.17.3 | . . . 65.16.3 ไม่อนุมัติแจ้งซ่อม(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Back-end |  | 2023-06-19 | 2023-06-23 | 5 | 80% | 5 | Waiting for Interface
3.2.17.4 | . . . 65.16.4 ยืนยันอนุมัติแจ้งซ่อม | Nai |  | Back-end |  | 2023-06-19 | 2023-06-23 | 5 | 80% | 5 | Waiting for Interface
3.2.18 | 65.17 บันทึกปิดงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.18.1 | . . . 65.17.1 บันทึกปิดงาน | Nai |  | Back-end |  | 2023-06-26 | 2023-06-30 | 5 | 80% | 5 | Waiting for Interface
3.2.19 | 65.18 ตรวจรับงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.19.1 | . . . 65.18.1 ตรวจรับงาน | Nai |  | Back-end |  | 2023-06-26 | 2023-06-30 | 5 | 80% | 5 | Waiting for Interface
3.2.20 | 65.19 รายการประวัติการแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
3.2.20.1 | . . . 65.19.1 รายละเอียดประวัติแจ้งซ่อม | Nai |  | Back-end |  | 2023-06-26 | 2023-06-30 | 5 | 80% | 5 | Waiting for Interface
3.2.20.2 | . . . 65.19.2 รายละเอียดประวัติแจ้งซ่อมตามครุภัณฑ์ | Nai |  | Back-end |  | 2023-06-26 | 2023-06-30 | 5 | 80% | 5 | Waiting for Interface
3.2.21 | 65.20 Mail Template | Aof | Nai | Back-end |  | 2023-05-08 | 2023-05-12 | 5 | 80% | 5 | Waiting for Interface
3.2.22 | 65.21 Master Data | Aof | Nai | Back-end |  | 2023-05-15 | 2023-05-19 | 5 | 80% | 5 | Waiting for Interface
4 | Testing Phase : System Integrate Test (SIT) | [5 empty] | - |  | 0% | - | bar: 2022-11-21 to 2023-01-15
4.1 | Provide SIT Document | New | All | All |  | 2023-05-22 | 2023-05-24 | 3 | 0% | 3 | To-Do
4.2 | System Integrate Test | New | All | All |  | 2023-05-25 | 2023-06-09 | 16 | 0% | 12 | To-Do
4.3 | Fix Bugs & Issues | New | All | All |  | 2023-05-30 | 2023-06-16 | 18 | 0% | 14 | To-Do
5 | Testing Phase : User Acceptance Test (UAT) | [5 empty] | - |  | 0% | - | bar: 2022-11-21 to 2023-01-15
5.1 | Provide UAT Environment | New | All | DepOps |  | 2023-05-22 | 2023-05-24 | 3 | 0% | 3 | To-Do
5.2 | UAT Environment : Software Installation | New | All | DepOps |  | 2023-05-22 | 2023-05-24 | 3 | 0% | 3 | To-Do
5.3 | UAT Environment : Data Cleansing | New | All | All |  | 2023-05-22 | 2023-06-02 | 12 | 0% | 10 | To-Do
5.4 | UAT Environment : Data Migration | New | All | All |  | 2023-05-22 | 2023-06-02 | 12 | 0% | 10 | To-Do
5.5 | Provide User Acceptance Test Document | New | All | SA |  | 2023-05-22 | 2023-05-24 | 3 | 0% | 3 | To-Do
5.6 | User Acceptance Test | All |  | All |  | 2023-06-05 | 2023-06-16 | 12 | 0% | 10 | To-Do
5.7 | Fix Bugs & Issues | All |  | All |  | 2023-06-12 | 2023-06-23 | 12 | 0% | 10 | To-Do
6 | Production Preparation&Deployment Phase | [5 empty] | - |  | 0% | - | bar: 2022-11-21 to 2023-01-15
6.1 | Provide Production Environment | New | All | DepOps |  | 2023-05-25 | 2023-05-29 | 5 | 0% | 3 | To-Do
6.2 | Production Environment : Software Installation | New | All | DepOps |  | 2023-05-25 | 2023-05-27 | 3 | 0% | 2 | To-Do
6.3 | Production Environment : Data Cleansing | New | All | All |  | 2023-06-26 | 2023-07-07 | 12 | 0% | 10 | To-Do
6.4 | Production Environment : Data Migration | New | All | All |  | 2023-06-26 | 2023-07-07 | 12 | 0% | 10 | To-Do
7 | Training Phase | [5 empty] | - |  | 0% | - | bar: 2022-11-21 to 2023-01-15
7.1 | User Training Document | New | Puen | SA |  | 2023-07-10 | 2023-07-11 | 2 | 0% | 2 | To-Do
7.2 | Admin Training Document | New | Puen | SA |  | 2023-07-12 | 2023-07-13 | 2 | 0% | 2 | To-Do
7.3 | User Training | Puen |  | Lead |  | 2023-07-17 | 2023-07-17 | 1 | 0% | 1 | To-Do
7.4 | Admin Training | Puen |  | Lead |  | 2023-07-18 | 2023-07-18 | 1 | 0% | 1 | To-Do
7.5 | Deliverable Document | New | Puen | SA |  | 2023-07-19 | 2023-07-21 | 3 | 0% | 3 | To-Do
8 | Deployment Phase | [5 empty] | - |  | 0% | - | bar: 2022-11-21 to 2023-01-15
8.1 | Go-live preparation | Guitar |  | DepOps |  | 2023-07-22 | 2023-07-22 | 1 | 0% | 0 | To-Do
8.2 | Go-live | All |  | All |  | 2023-07-23 | 2023-07-23 | 1 | 0% | 0 | To-Do
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] | [5 empty] | - |  |  | -
1.1 | . [ Level 2 Task ] | [5 empty] | - |  |  | -
1.1.1 | . . [ Level 3 Task ] | [5 empty] | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] | [5 empty] | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Lead Enter the name of the Task Lead in this column.
Note on F7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on G7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on H7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on I7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## SQL Server
Asset Management
Top provider systems & supply co.,ltd
| Project Start Date |  |  | 2022-11-25 |  |  |  | Display Week | 1 |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23
| Project Overall Percentage |  |  | 0% | #DIV/0! | #DIV/0! | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12 | [6 empty] | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24
 | time axis 2022-11-21 to 2023-04-30
WBS | TASK | Assignee1 | Assignee2 | Team | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | Owner | Status | time axis 2022-11-21 to 2023-04-30
1 | Development Phase | [5 empty] | - |  |  | - | bar: 2022-11-21 to 2023-01-15
1.1 | Back-end | [7 empty] | 0% | bar: 2022-11-21 to 2023-01-15
1.1.1 | 65.0 เข้าสู่ระบบ | bar: 2022-11-21 to 2023-01-15
1.1.1.1 | . . . 65.0.0 เข้าสู่ระบบ | Aof |  | Back-end |  | 2023-08-04 | 2023-08-04 | 1 | 0% | 1 |  | To-Do
1.1.1.2 | . . . 65.0.1 ลืมรหัสผ่าน | Aof |  | Back-end |  | 2023-08-05 | 2023-08-05 |  | 0% | 0 |  | To-Do
1.1.2 | 65.1 dashboard งานบริหารงานทรัพย์สิน | bar: 2022-11-21 to 2023-01-15
1.1.2.1 | . . . 65.1.1 dashboard งานซ่อม | Aof |  | Back-end |  | 2023-08-06 | 2023-08-06 |  | 0% | 0 |  | To-Do
1.1.3 | 65.2 รายการข้อมูลครุภัณฑ์ | bar: 2022-11-21 to 2023-01-15
1.1.3.1 | . . . 65.2.1 บันทึกครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.3.2 | . . . 65.2.2 ดูรูปภาพเพิ่มเติมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.3.3 | . . . 65.2.3 คู่มือ/เอกสารแนบครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.3.4 | . . . 65.2.4 ค่าเสื่อมราคาครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.3.5 | . . . 65.2.5 รายละเอียดข้อมูลครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-13 | 2023-07-13 |  | 0% | 1 |  | To-Do
1.1.3.6 | . . . 65.2.7 แก้ไขข้อมูลครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-13 | 2023-07-13 |  | 0% | 1 |  | To-Do
1.1.3.7 | . . . 65.2.8 ลบข้อมูลครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-13 | 2023-07-13 |  | 0% | 1 |  | To-Do
1.1.4 | 65.3 ข้อมูลครุภัณฑ์หน่วยงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.4.1 | . . . 65.3.1 ดูข้อมูลครุภัณฑ์หน่วยงาน | Nai |  | Back-end |  | 2023-07-13 | 2023-07-13 |  | 0% | 1 |  | To-Do
1.1.5 | 65.4 รายการข้อมูลครุภัณฑ์เป็นชุด | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.5.1 | . . . 65.4.1 บันทึกครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.5.2 | . . . 65.4.2 ดูรูปภาพเพิ่มเติมครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.5.3 | . . . 65.4.3 ส่วนประกอบย่อยครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.5.4 | . . . 65.4.4 คู่มือ/เอกสารแนบครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.5.5 | . . . 65.4.5 ค่าเสื่อมราคาครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.5.6 | . . . 65.4.6 รายละเอียดข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.5.7 | . . . 65.4.7 แก้ไขข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-12 | 2023-07-12 |  | 0% | 1 |  | To-Do
1.1.5.8 | . . . 65.4.8 ลบข้อมูลครุภัณฑ์เป็นชุด | Nai |  | Back-end |  | 2023-07-11 | 2023-07-11 |  | 0% | 1 |  | To-Do
1.1.6 | 65.5 ข้อมูลครุภัณฑ์เป็นชุด(หน่วยงาน) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.6.1 | . . . 65.5.1 ดูข้อมูลครุภัณฑ์เป็นชุด(หน่วยงาน) | Nai |  | Back-end |  | 2023-07-12 | 2023-07-12 |  | 0% | 1 |  | To-Do
1.1.7 | 65.6 รายการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.7.1 | . . . 65.6.1 รายละเอียดโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-14 | 2023-07-14 |  | 0% | 1 |  | To-Do
1.1.7.2 | . . . 65.6.2 บันทึกโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-14 | 2023-07-14 |  | 0% | 1 |  | To-Do
1.1.7.3 | . . . 65.6.3 แก้ไขโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-17 | 2023-07-17 |  | 0% | 1 |  | To-Do
1.1.7.4 | . . . 65.6.4 ยกเลิกโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-17 | 2023-07-17 |  | 0% | 1 |  | To-Do
1.1.8 | 65.7 รายการอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.8.1 | . . . 65.7.1 รายละเอียดขออนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-18 | 2023-07-18 |  | 0% | 1 |  | To-Do
1.1.8.2 | . . . 65.7.2 รายละเอียดการอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-18 | 2023-07-18 |  | 0% | 1 |  | To-Do
1.1.8.3 | . . . 65.7.3 ไม่อนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์(สาเหตุแบบหลายรายการ) | Nai |  | Back-end |  | 2023-07-18 | 2023-07-18 |  | 0% | 1 |  | To-Do
1.1.8.4 | . . . 65.7.4 ไม่อนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Back-end |  | 2023-07-18 | 2023-07-18 |  | 0% | 1 |  | To-Do
1.1.8.5 | . . . 65.7.5 ยืนยันอนุมัติโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-19 | 2023-07-19 |  | 0% | 1 |  | To-Do
1.1.8.6 | . . . 65.7.6 แก้ไขรายการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-19 | 2023-07-19 |  | 0% | 1 |  | To-Do
1.1.9 | 65.8 ประวัติการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.9.1 | . . . 65.8.1 รายละเอียดประวัติการโอน/ย้ายสถานที่ตั้งครุภัณฑ์ | Aof |  | Back-end |  | 2023-07-19 | 2023-07-19 |  | 0% | 1 |  | To-Do
1.1.10 | 65.9 รายการยืม-คืนครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.10.1 | . . . 65.9.1 รายละเอียดการยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-20 | 2023-07-20 |  | 0% | 1 |  | To-Do
1.1.10.2 | . . . 65.9.2 บันทึกใบยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-20 | 2023-07-20 |  | 0% | 1 |  | To-Do
1.1.10.3 | . . . 65.9.3 บันทึกใบคืนครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-20 | 2023-07-20 |  | 0% | 1 |  | To-Do
1.1.10.4 | . . . 65.9.4 แก้ไขใบยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-21 | 2023-07-21 |  | 0% | 1 |  | To-Do
1.1.10.5 | . . . 65.9.5 ยกเลิกใบยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-21 | 2023-07-21 |  | 0% | 1 |  | To-Do
1.1.11 | 65.10 รายการอนุมัติยืมครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.11.1 | . . . 65.10.1 รายละเอียดอนุมัติยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-24 | 2023-07-24 |  | 0% | 1 |  | To-Do
1.1.11.2 | . . . 65.10.2 รายละเอียดการอนุมัติยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-24 | 2023-07-24 |  | 0% | 1 |  | To-Do
1.1.11.3 | . . . 65.10.3 ไม่อนุมัติยืมครุภัณฑ์(สาเหตุแบบหลายรายการ) | Nai |  | Back-end |  | 2023-07-24 | 2023-07-24 |  | 0% | 1 |  | To-Do
1.1.11.4 | . . . 65.10.4 ไม่อนุมัติยืมครุภัณฑ์(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Back-end |  | 2023-07-25 | 2023-07-25 |  | 0% | 1 |  | To-Do
1.1.11.5 | . . . 65.10.5 ยืนยันอนุมัติยืมครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-25 | 2023-07-25 |  | 0% | 1 |  | To-Do
1.1.12 | 65.11 ประวัติการยืมครุภัณฑ์(ตามเลขที่ใบยืมครุภัณฑ์) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.12.1 | . . . 65.11.1 รายละเอียดประวัติการยืม(ตามเลขที่ใบยืมครุภัณฑ์) | Nai |  | Back-end |  | 2023-07-25 | 2023-07-25 |  | 0% | 1 |  | To-Do
1.1.13 | 65.12 รายการตรวจรับคืนครุภัณฑ์ | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.13.1 | . . . 65.12.1 ตรวจรับการคืนครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-26 | 2023-07-26 |  | 0% | 1 |  | To-Do
1.1.13.2 | . . . 65.12.2 รายละเอียดการตรวจรับคืนครุภัณฑ์ | Nai |  | Back-end |  | 2023-07-26 | 2023-07-26 |  | 0% | 1 |  | To-Do
1.1.14 | 65.13 รายการแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.14.1 | . . . 65.13.1 บันทึกรายการแจ้งซ่อม | Nai |  | Back-end |  | 2023-07-26 | 2023-07-26 |  | 0% | 1 |  | To-Do
1.1.14.2 | . . . 65.13.2 แก้ไขรายการแจ้งซ่อม | Nai |  | Back-end |  | 2023-07-26 | 2023-07-26 |  | 0% | 1 |  | To-Do
1.1.14.3 | . . . 65.13.3 ยกเลิกรายการแจ้งซ่อม(กรณียังไม่รับงาน) | Nai |  | Back-end |  | 2023-07-27 | 2023-07-27 |  | 0% | 1 |  | To-Do
1.1.14.4 | . . . 65.13.4 รายละเอียดการแจ้งซ่อม | Nai |  | Back-end |  | 2023-07-27 | 2023-07-27 |  | 0% | 1 |  | To-Do
1.1.15 | 65.14 รายการแจ้งซ่อม(ศูนย์ซ่อม) | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.15.1 | . . . 65.14.1 ดูรายละเอียดแจ้งซ่อม/รับงานแจ้งซ่อม | Nai |  | Back-end |  | 2023-07-27 | 2023-07-27 |  | 0% | 1 |  | To-Do
1.1.15.2 | . . . 65.14.1.1 ไม่รับงาน | Nai |  | Back-end |  | 2023-07-28 | 2023-07-28 |  | 0% | 1 |  | To-Do
1.1.15.3 | . . . 65.14.2 ลงบันทึกแจ้งซ่อม | Nai |  | Back-end |  | 2023-07-28 | 2023-07-28 |  | 0% | 1 |  | To-Do
1.1.15.4 | . . . 65.14.3 จ้างซ่อมภายนอก | Nai |  | Back-end |  | 2023-07-28 | 2023-07-28 |  | 0% | 1 |  | To-Do
1.1.15.5 | . . . 65.14.4 แก้ไขแจ้งซ่อม | Nai |  | Back-end |  | 2023-07-31 | 2023-07-31 |  | 0% | 1 |  | To-Do
1.1.16 | 65.15 รายการตรวจสอบจ้างซ่อมภายนอก | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.16.1 | . . . 65.15.1 รายละเอียดจ้างซ่อมภายนอก | Nai |  | Back-end |  | 2023-07-31 | 2023-07-31 |  | 0% | 1 |  | To-Do
1.1.17 | 65.16 รายการอนุมัติแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.17.1 | . . . 65.16.1 ข้อมูลอนุมัติการแจ้งซ่อม | Nai |  | Back-end |  | 2023-07-31 | 2023-07-31 |  | 0% | 1 |  | To-Do
1.1.17.2 | . . . 65.16.2 ไม่อนุมัติแจ้งซ่อม(สาเหตุแบบหลายรายการ) | Nai |  | Back-end |  | 2023-08-01 | 2023-08-01 |  | 0% | 1 |  | To-Do
1.1.17.3 | . . . 65.16.3 ไม่อนุมัติแจ้งซ่อม(แยกการให้สาเหตุแต่ละรายการ) | Nai |  | Back-end |  | 2023-08-01 | 2023-08-01 |  | 0% | 1 |  | To-Do
1.1.17.4 | . . . 65.16.4 ยืนยันอนุมัติแจ้งซ่อม | Nai |  | Back-end |  | 2023-08-01 | 2023-08-01 |  | 0% | 1 |  | To-Do
1.1.18 | 65.17 บันทึกปิดงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.18.1 | . . . 65.17.1 บันทึกปิดงาน | Nai |  | Back-end |  | 2023-08-02 | 2023-08-02 |  | 0% | 1 |  | To-Do
1.1.19 | 65.18 ตรวจรับงาน | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.19.1 | . . . 65.18.1 ตรวจรับงาน | Nai |  | Back-end |  | 2023-08-02 | 2023-08-02 |  | 0% | 1 |  | To-Do
1.1.20 | 65.19 รายการประวัติการแจ้งซ่อม | [8 empty] | - | bar: 2022-11-21 to 2023-01-15
1.1.20.1 | . . . 65.19.1 รายละเอียดประวัติแจ้งซ่อม | Nai |  | Back-end |  | 2023-08-02 | 2023-08-02 |  | 0% | 1 |  | To-Do
1.1.20.2 | . . . 65.19.2 รายละเอียดประวัติแจ้งซ่อมตามครุภัณฑ์ | Nai |  | Back-end |  | 2023-08-03 | 2023-08-03 |  | 0% | 1 |  | To-Do
1.1.21 | 65.20 Mail Template | Aof | Nai | Back-end |  |  | - |  | 0% | - |  | To-Do
1.1.22 | 65.21 Master Data | Aof | Nai | Back-end |  | 2023-08-03 | 2023-08-03 |  | 0% | 1 |  | To-Do
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] | [5 empty] | - |  |  | -
1.1 | . [ Level 2 Task ] | [5 empty] | - |  |  | -
1.1.1 | . . [ Level 3 Task ] | [5 empty] | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] | [5 empty] | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Lead Enter the name of the Task Lead in this column.
Note on F7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on G7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on H7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on I7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## Sheet1
บันทึกครุภัณฑ์ | บันทึกครุภัณฑ์ save draft ยังติดปัญหา API แนบไฟล์ไม่ได้
บันทึกครุภัณฑ์(ชุด) | บันทึกครุภัณฑ์(ชุด) save draft ยังติดปัญหา API แนบไฟล์ไม่ได้
ถามนะนายเรื่อง forgot password
dashboard งานซ่อม

## Master Plan (hidden)
PROJECT PLAN
TTM CRANE | 2022-12-02 |  |  |  | 2023-01-02 |  |  |  | 2023-02-02 |  |  |  | 2023-03-02 |  |  |  | 2023-04-02 |  |  |  | 2023-05-02
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1. Kick-off meeting. | bar: 2022-12-02 W3
2. Requirement Gathering. | bar: 2023-01-02 W1 to 2023-01-02 W2
3. Analysis and Design. | bar: 2023-01-02 W2 to 2023-01-02 W3
4. Development. | bar: 2023-01-02 W2 to 2023-04-02 W2
5. Sprint Update and Get Feedback. | bar: 2023-01-02 W3; 2023-02-02 W1; 2023-02-02 W3; 2023-03-02 W1; 2023-03-02 W3; 2023-04-02 W1 to 2023-04-02 W2
6. User Acceptance Test. | bar: 2023-04-02 W2 to 2023-04-02 W4
7. Document and Training. | bar: 2023-04-02 W4 to 2023-05-02 W1
8. Go-live. | bar: 2023-05-02 W2
Kick of meeting.
Go-live
วันหยุดสิ้นปี

## Master Data
Team | Assignee | To-Do | Project Growth Chart (%)
Front-end | Puen | In-Progress | 2022-11-30 | 0%
Back-end | New | Waiting for Test | 2022-12-07 | 0.37%
Lead | Guitar | Passed | 2022-12-14 | 0.75%
UX/UI | Memmos | Re-work | 2022-12-21 | 1.03%
SA | Nai | Completed | 2022-12-28 | 1.12%
DepOps | Guy | Waiting for Interface | 2023-01-04 | 1.19%
All | Aof |  | 2023-01-11 | 1.25%
| All |  | 2023-01-18 | 4.5%
|  |  | 2023-01-25 | 4.5%
|  |  | 2023-02-01 | 6.04%
|  |  | 2023-02-08 | 8.21%
|  |  | 2023-02-15 | 23.38%
|  |  | 2023-02-22 | 26.24%
|  |  | 2023-03-01 | 30.9%
|  |  | 2023-03-08 | 32.78%
|  |  | 2023-03-15 | 41.73%
To-Do | 39 | 26% | 2023-04-05 | 42.71%
In-Progress | 3 | 2% | 2023-04-19 | 46.09%
Waiting for Test | 44 | 29.33% | 2023-06-14 | 56.47%
Passed | 0 | 0% | 2023-06-28 | 69.78%
Re-work | 0 | 0% | 2023-07-05
Completed | 6 | 4% | 2023-07-12
2023-07-19
2023-07-26
|  | Project Overall Percentage | 2023-08-02
Percentage | 30.22% | 69.78% | 2023-08-09
Total | 100% |  | 2023-08-16
2023-08-23
2023-08-30
2023-09-06
2023-09-13

## GanttChartPro (hidden)
Gantt Chart Template Pro
Gantt Chart Template Pro is similar to this free version, but
it is more feature-packed. It also comes with other bonus content.
Learn About Gantt Chart Template Pro
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
The following link is a blog post that talks specifically about the
Pro version for Excel Online.
Gantt Chart Template Pro for Excel Online
Benefits and Features of Gantt Chart Template Pro
Simple Color-Coding
The Pro version includes a column for specifying the color of bars in the chart. For example,
you could change the color based on urgency or task lead.
Daily, Weekly, or Monthly View
The Pro version includes a drop-down next to the Display Week that lets you choose to display
the columns in the chart area as days, weeks, or months.
Use Work Days as an Input
By default, the Pro version is set up to have you enter Work Days instead of Calendar Days.
The expanded set of template rows provides more options for defining the Start date, End date,
and Duration of tasks. Define a task based on …
- Start date and End date
- Start date and Work days
- Start date and Calendar days
Easily Create Task Dependencies
Though you can still use your own formulas for creating task dependencies, the Pro version
includes template rows that calculate the Start date based on the WBS number that you enter
in the Predecessor column.
Exclude Holidays from Work Days
List holidays and other specific non-working days that you want to exclude from work days.
Customize Your Work Week
The versions designed for Excel 2010+ use the WORKDAY.INTL() and NETWORKDAYS.INTL()
functions that allow you define the work week as something other than Monday-Friday.
Learn More About Gantt Chart Template Pro

## Help (hidden)
Help
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
About This Template
This Gantt Chart Template provides an easy way to create a simple project schedule. You only need to know some basic spreadsheet operations, such as how to insert, delete, copy and paste rows and cells. For more advanced uses, such as defining task dependencies, you will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. Watching the video demos for Gantt Chart Template Pro may also help you see how to use the spreadsheet.
Watch Demo Videos of the Pro Version on Vertex42.com
Please read the license agreement in the TermsOfUse worksheet to learn how you may or may not use and share this spreadsheet.
Getting Started Tips
• [Bracketed Text] is meant to be edited, like the project title and task descriptions.
| • Some of the labels include cell comments to provide extra information. | Label
• To adjust the range of dates shown in the Gantt chart, change the Display Week number.
• The Project Start Date is used to define the first week shown in the gantt chart.
• Insert new tasks using one of the methods listed below.
| • Define the task start date and duration (days) by editing the light green cells. | Input Cell
• If you see "#####" in a cell, widen the column to display the cell contents.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Inserting New Tasks (Rows)
When inserting and deleting tasks, you need to insert and delete entire rows. Some columns contain formulas (such as the End Date and the Work Days columns), so these formulas need to copied to the newly inserted rows.
METHOD 1 (recommended)
• Insert a new blank row by right-clicking on the row number and selecting Insert.
• With the new blank row selected, press Ctrl+d to copy the formulas and formatting down from the row above OR use the row drag handle to copy the formulas and formatting down.
METHOD 2
• Copy a row from the set of template rows at the bottom of the worksheet.
• Right-click on the row where you want to insert the new task and select Insert Copied Cells.
Method 2 will work, but Excel will split/fracture/duplicate conditional formatting rules rather than merging the rules. This can cause inefficiencies in very large and heavily modified files.
Help improve Excel by voting on a suggestion to fix this problem.
Using the Template Rows and Choosing a WBS Level
The set of template rows at the bottom of the Gantt Chart worksheet provide examples of different ways to format and define tasks for different WBS levels.
Each different WBS level uses a different formula in the WBS column.
You can either copy/paste/insert these template rows via Method 2 as explained above, OR you can just copy/paste the desired WBS cell when you want to change the WBS level.
If you leave a blank cell above a WBS number, the numbering will reset to 1.x.x. The formulas are meant for convenience, but you can manually enter the WBS numbers if you want to.
You can indent the task description for sub-tasks by entering leading spaces or using the Indent feature in Excel.
Creating Task Dependencies
You can enter the Start date manually, or define task dependencies using a formula. Below are some common options for defining the Start date:
A. | Enter the date manually (e.g. 1/3/2015)
B. | Reference the Project Start Date (e.g. =$E$4 )
C. | Set the Start date to the next Work Day after another task's End date.
• Use the formula =WORKDAY(enddate,1) where enddate is the reference to the End date of a predecessor task.
• For multiple predecessors, the formula would be =MAX(WORKDAY(enddate1,1),WORKDAY(enddate2,1))
D. | Set the Start date to the next Calendar Day after another task's End date.
• This formula is very simple: =enddate+1
• For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
E. | Set the Start date to a number of days before or after another date.
• This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY(enddate,5) or =WORKDAY(startdate,-5)
F. | Use a lookup formula and the Predecessor column to define the start date.
[The formulas for using this method are built into Gantt Chart Template Pro]
Changing the Color of the Bars in the Gantt Chart
[Advanced] The Gantt Chart is created using conditional formatting, so you can modify the conditional formatting rules to change the format to a different color. The Pro version includes a column where you can change the color by entering a color code ("b"=blue, "g"=green, etc.)
FAQs
Q: | How do I enter the Work Days instead of Calendar Days?
Entering work days instead of calendar days is a feature of the Pro version. There is nothing in the free version preventing you from entering your own formulas, though.
Q: | How do I calculate Calendar Days after entering the Start and End Dates?
You can calculate the duration in calendar days (including both start and end dates) using the formula =enddate-startdate+1
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and Page Orientation as desired.
Q: | How do I increase the range of dates displayed in the Gantt chart?
You will need to add columns to the right of the Gantt Chart via copy/paste. Copy and paste the columns in groups of 7. Afterwards, you will also probably need to update the print area.
Q: | How do I create a summary row that shows the MIN and MAX dates for all sub-tasks?
In the Start column, use the formula =MIN(range_of_start_dates)
In the End column, use the formula =MAX(range_of_end_dates)
In the Days column, use the formula =end_date-start_date+1
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a group of tasks can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2018 Vertex42 LLC
Note on C16: This is an example comment.

## TermsOfUse (hidden)
Terms of Use
Gantt Chart Template, by Vertex42.com
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
© 2006-2018 Vertex42 LLC
This spreadsheet template, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
You may download the spreadsheet template, make archival copies, and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any Vertex42 logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template.
The template and any file, document, or other work including or derived from the template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on any server in a way that makes it available to the general public.
Limited Private Sharing and Other Allowed Uses: See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html